## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | SPRINT REVIEW
User Story #1
AdressGenerator | 5 | Brandon | Done | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Location | 3 | Francis | Done | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Route | 5 | Jorge | Done | 1 | 0 | 0.5 | 1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LocationMapDisplay | 9 | Brandon | Done | 4 | 0 | 0 | 0.5 | 5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
UML | 2 | Brandon | Done | 0.5 | 0.5 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
User Story #2
AddressGenerator | 3 | Brandon | Done | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
UML | 2 | Brandon | Done | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Route | 5 | Jorge | in Progress | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 2
Simulation | 9 | Brandon | in Progress | 4.5 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 2
Location | 3 | Francis | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
Truck | 3 | Francis | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 21.5 | 2.5 | 2 | 1.5 | 7.6 | 2.6 | 0.5 | 3.5 | 4 | 3 | 3 | 4